30/05/2023

Data
done:
The formated Italian data will be initially usefull for exploring temporal networks

to do:
BDNI data -> probably obtaining data through the ANSES/Spie BDNI access agreement (via Viviane) will be the most appropriate. I will arange a meeting in the coming weeks (?) as a first step. I have already dealt on cleaning, transforming, reorgnizaing and storing BDNI data before starting my PhD, so this could be of benefit to me.

Network
done:
Continuation of the bibliography with information given during Thursday's visio meeting

to do:
elaborate a first toy model

Epidemiological modelling
done:
just an overview of litterature on AMR modelling (not yet exhaustive). This point will be need to be clarified in a second stage

to do:
everithing !

miscellaneous

correction according to the revisions provided by the reviewers of the submit article "Coupling spatial and temporal structure in batch rearing modelling fot understanding the spread of the swine influenza A virus" in PVM IA (special issue)

submission of the article "Pig herd management and infection transmission dynamics: a challenge for modellers" to PCI Animal Science

I might have another publication in the pipeline on theoretical concepts of agent-based modelling and simulation, following on from my PhD work. That would be great, but there's no rush.
2/06/2023

Data
done:
used Italian data to develop two toy models

to do:
organize a meeting with ANSES for BDNI

Network
done:
Developed two initial toy models (one in Python and the other in C++) based on Italian data.
Continued working on the bibliography.

to do:
Improve the toy models and explore the results

Epidemiological modelling
done:

to do:

miscellaneous

visit to the lab on Wednesday.
Medical visit scheduled for Thursday.
Waiting for the signed agreement.